## Reprint table . Complete table
Feature | Task Description | Definition of Done
Validate and Choose ADO Security Controls | Identify Relevant ADO Security Controls | * A list of relevant ADO security controls is identified, covering areas like access control, auditing, and secrets management.
| Evaluate Control Effectiveness Against Security Requirements | * Each control is evaluated to determine its effectiveness in meeting specific security requirements for the project/environment.
| Document Control Validation Process and Recommendations | * A document is created outlining the control validation process, the evaluation results, and recommendations for implementing or adjusting ADO security controls.
Infrastructure and Configuration | Define VM Specifications (OS, resources) for Security Scanner. | * Documented list of VM requirements (OS version, CPU, memory, storage) is available.
| Procure Virtual Machine for Security Scanner. | * VM is procured and meets the defined specifications. * VM is accessible for configuration and use.
| Configure Network Access for Security Scanner VM. | * VM has necessary network access to ADO resources and scan targets. * Security best practices are followed for network configuration.
| Create Service Account with Limited Privileges. | * Service account is created with minimal permissions required for security scanner execution. * Service account credentials are stored securely (e.g., Azure Key Vault).
| Securely Store Service Account Credentials. | * Service account credentials are encrypted and stored in a secure location with access controls.
Security Scanner Policy Configuration | Identify Target Applications/Repositories for Scanning. | * List of applications/repositories to be scanned is finalized.
| Define Security Scanner Policy Settings (severity levels, exclusions). | * Security scanner policy is created with desired settings for scan behavior (severity levels, exclusion patterns).
| Integrate Security Scanner Policy with CI/CD Pipeline. | * Security scanner policy is linked to the chosen CI/CD pipeline for automated execution.
Batch Script Development and Integration | Develop Batch Script for ADO Service Account Authentication. | * Batch script is developed to authenticate with ADO using the service account credentials.
| Implement Security Scanner Trigger within Batch Script. | * Script includes a command to trigger the security scan based on the configured policy.
| Configure Batch Script for Security Scan Result Capture and Storage. | * Script captures security scan results and stores them in a designated location (e.g., local storage, shared folder).
| Integrate Batch Script with CI/CD Pipeline for Scheduled Execution. | * Batch script is integrated with the CI/CD pipeline for scheduled security scan execution.
Security Scan Result Processing and Analysis | Define Process for Security Scan Result Review. | * A documented process outlines steps for reviewing security scan results after each execution.
| Develop System for Vulnerability Categorization and Prioritization. | * A system is implemented to categorize vulnerabilities based on severity, exploitability, and impact. * A prioritization scheme is defined for addressing vulnerabilities based on risk.
| Create Plan for Addressing Vulnerabilities Based on Severity. | * A plan is established that outlines actions for remediating vulnerabilities based on their severity (e.g., patching, code fix).
| Document Security Scan Result Processing Procedures. | * A comprehensive document details the process for handling security scan results, including review, categorization, and remediation planning.
Security Scan Dashboard Development and Integration | Define Key Metrics and Visualizations for Security Scan Dashboard. | * A document specifies the key metrics (total vulnerabilities, severity distribution, trends) and visualizations required for the dashboard.
| Select Dashboarding Tool Compatible with Backend Storage. | * A suitable dashboarding tool is chosen that integrates with the chosen backend storage solution for security scan results.
| Develop Security Scan Dashboard with Filtering and Drill-Down Features. | * The security scan dashboard is developed based on defined requirements, allowing users to filter and explore data for detailed analysis.
| Integrate Security Scan Dashboard with ADO Platform. | * The security scan dashboard is integrated into the ADO platform for easy access by users.
Alerting for High-Severity Vulnerabilities | Define Severity Criteria for Triggering Security Alerts. | * Criteria are established for triggering alerts based on the severity of identified vulnerabilities (e.g., "High" or "Critical").
| Choose Alert Notification Channel (e.g., email, SMS, Slack). | * An appropriate notification channel is selected to ensure timely delivery of alerts for high-severity vulnerabilities.